## Skills
Skills
Skills | Name
XML, SQL, C++, C | Guangchu Shi
Java, Spring, Herbnate, OOP, MySQL | Hongquan Yu
Java, Spring, MySQL, AWS, Project Management, Git | Ribe Ninan
Java, MySQL, JDBC, AWS, Testing | Xiangfeng Wang
AWS,Java,Bootstrap(html+css), Frontend(Design),Git,MySQL | Yue Wang
Design, Testing, HTML, CSS, JavaScript | Zeqian Huang

## Roles and Responsibilities
Roles and Responsibilities
Title | Member (Primary, Backup) | Responsibilities
Project Manager | Ribe Ninan | Primarily: Communication with the instructor, creating and maintaining the project plan, maintaining backlog, tracking project hours and implemention of the LMS application | Note: All team members need contribute in both development,and validation(every stage of the software design). The roles listed are the primary responsibility of the member.
Architecture Lead | Guangchu Shi | Primarily: Determining the architecture/module for the system to meet the business needs/stakeholder requirements
UI lead | Zeqian Huang | Primarily: Develop Front-End UI for the application, and implement Java code to work with the Front End
Design lead | Emily Wang | Primarily: design the details for the modules
Implementation Lead | Hongquan Yu | Primarily: implement the system according to the design
Test Lead | Xiangfeng Wang | Primarily: Test the system against requirement

## Estimation
Effort Estimation and Tracking
Effort (Person hours)
MAIN ACTIVITY | Sub-tasks | Guangchu Shi |  | Hongquan Yu |  | Ribe Ninan |  | Xiangfeng Wang |  | Yue Wang |  | Zeqian Huang |  | TOTAL ESTIMATED EFFORT per activity | TOTAL ACTUAL EFFORT per activity
Project Plan |  | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual
| Team Meeting | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6
| Skills Section | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 3 | 3
| Roles and Responsibilities | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 1 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 3 | 3
| Estimation | 0.25 | 0.25 | 0.25 | 0.25 | 3 | 3 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 5 | 5
| Project Environment | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 2.5 | 1 | 1.5 | 0.25 | 0.25 | 0.25 | 0.25 | 3 | 5
| Risk Analysis and Management | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 2 | 2 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 5 | 7
| Team Operating Procedures | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 1 | 2 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 6 | 4
| Team Review | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0.5 | 2 | 2
Requirements Analysis | Team Meeting | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6
| Abuse Case Model | 1 | 1 | 7 | 10 | 1 | 1 | 1 | 1 | 8 | 9 | 1 | 1 | 19 | 23
| Abuse Case Model Review | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6
| Quality Utility Tree | 9 | 10 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 12 | 22 | 26
| Quality Utility Tree Review | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 8 | 8
TOTAL ESTIMATED and ACTUAL EFFORT per student |  | 15.5 | 16.5 | 15.5 | 18.5 | 16 | 17.5 | 15 | 15.5 | 16.5 | 17.5 | 15.5 | 18.5 | 94 | 104

## Project Environment
Project Environment
Management/Collaboration/Communication Activity | Selected Tool(s)
Project Documents | Google Drive
Backlog, Estimations, Team Status Tracking | Trello
Communication | GroupMe
Engineering Activity | Selected Tool(s)
Language Framework | Java, Spring, JSP, JavaScript, Bootstrap, HTML, CSS
Version Control | Github
Database | MySQL hosted on AWS
DAO | JDBC
Web Hosting | AWS EC2
IDE | Eclipse/Netbeans
Dependency Management | Maven
Testing | Selenium, JUnit

## Risk Analysis and Management
Risk Analysis and Management
Risk description | Probability (Low=1, Medium=2, High=3) | Impact (Low=1, Medium=2, High=3) | Score (Probability x Impact) | Top 5 Priority Risks | Mitigation actions
|  |  |  | Unclear/Vague Requirements | Discuss unclear requirements with Stakeholder.
Technical Risk |  |  |  | Design Mistakes | Members will ensure that requirements are fully understood, designed (if needed), and discussed with the team before implementation to reduce the risk.
Unclear/Vague Requirements | 3 | 3 | 9 | Member absense due to illness/other reasons | If a team member cannot complete the work due to issues such as physical well being, then the team member will contact the PM, team members, as well as the instructor to provide a status update of their tasks.
Untracable Requirements | 1 | 2 | 2 | Scheduling Errors | During the weekly meetings, team members will go over the project deadlines, and the tasks that team members will complete for that week. The PM will ensure that the tasks are being completed appropriately.
Unmaintainable error prone code | 1 | 3 | 3 | Insufficient time estimation | Team members will disuss the estimation based both requirements and each member's experience each specific domain.
Design Mistakes | 3 | 3 | 9
Issues with environment/tools used for the project | 1 | 1 | 1
Management Risk
Scheduling Errors | 2 | 3 | 6
Insufficient time estimation | 3 | 2 | 6
Miscommunication between PM and members | 1 | 3 | 3
Unclear priorities | 3 | 1 | 3
People Risk
Member Turnover | 1 | 3 | 3
Member Poor Productivity | 1 | 3 | 3
Member absense due to illness | 2 | 3 | 6
Lack of experience | 2 | 3 | 6
Lack of ownership | 2 | 3 | 6

## Team Operating Procedures
Team Operating Procedures
How will the team communicate? | GroupMe for instant communication, in-person meeting twice a week.
How often? | Twice a week,one in classs and the other out of class
Meeting times? | Meeting in class before lecture, and second meeting at 4 pm on Thursday
How will the team collaborate? | Use google doc for documents. Github for version control
How are decisions made? | Team members will have a descussion and PM will make the final decision.
How are decisions documented? | PM will write the meeting notes and decisions on a document that is shared between the team members
…